## Task List
Week 6 Goal - Sell and Assessment pages done |  |  |  | Tasks to be sorted
| Location | Task | FE/BE | Location | Task | FE/BE
DONE | SELL | Finish design and layout | Front End | CAMPAIGN TILE | design and layout
| SELL | FD write up | Back End | CAMPAIGN TILE | FD write up |  | SELL | FD implementation
| SELL | FD code draft | Back End | CAMPAIGN TILE | FD code draft |  | ASSESSMENT | FD implementation
| ASSESSMENT | Finish design and layout | Front End | CAMPAIGN MODAL | design and layout |  | SIGN IN | FD implementation
| ASSESSMENT | FD write up | Back End | CAMPAIGN MODAL | FD write up |  | DASHBOARD | FD implementation
| ASSESSMENT | FD code draft | Back End | CAMPAIGN MODAL | FD code draft |  | CAMPAIGN TILE | FD implementation
|  |  |  | LEADS TILE | design and layout |  | CAMPAIGN MODAL | FD implementation
Week 5 Goal - |  |  |  | LEADS TILE | FD write up |  | LEADS TILE | FD implementation
| Location | Task | FE/BE | LEADS TILE | FD code draft |  | LEADS MODAL | FD implementation
| SIGN IN | Design and layout | Front End | LEADS MODAL | design and layout |  | ACQUISITION TILE | FD implementation
| SIGN IN | FD write up | Back End | LEADS MODAL | FD write up |  | ACQUISITION MODAL | FD implementation
| SIGN IN | FD code draft | Back End | LEADS MODAL | FD code draft |  | DISPOSITION TILE | FD implementation
| DASHBOARD | design and layout (kanban board) | Front End | ACQUISITION TILE | design and layout |  | DISPOSITION MODAL | FD implementation
| DASHBOARD | FD write up | Back End | ACQUISITION TILE | FD write up
| DASHBOARD | FD code draft | Back End | ACQUISITION TILE | FD code draft
|  |  |  | ACQUISITION MODAL | design and layout
Week 4 Goal - |  |  |  | ACQUISITION MODAL | FD write up
| Location | Task | FE/BE | ACQUISITION MODAL | FD code draft
|  |  |  | DISPOSITION TILE | design and layout
|  |  |  | DISPOSITION TILE | FD write up
|  |  |  | DISPOSITION TILE | FD code draft
|  |  |  | DISPOSITION MODAL | design and layout
|  |  |  | DISPOSITION MODAL | FD write up
|  |  |  | DISPOSITION MODAL | FD code draft

## Functionality Detail
SELL Functionality Detail
Type | Name | Task
BUTTON | submitBtn | Save fields to DB, push them to Assessment page
FIELD | Name | DB(Table: Contacts, Column: Name).
FIELD | County | DB(Table: Counties, Column: Name).
FIELD | State | DB(Table: Properties, Column: State).
FIELD | Phone | DB(Table: Contacts, Column: phone).
FIELD | Email | DB(Table: Contacts, Column: email).
BG | incomingDate | DB(Table: Leads, Column: leadAcquiredDate *Todays date*)
BG | propertyId | DB(Table: Leads, Column: propertyId *Created property row*)
BG | contactId | DB(Table: Leads, Column: contactId *created contact row*)
BG | Lead | DB(Table: Leads, Column: Status *Incoming*)
BG | County | DB(Table: Properties, Column: countyId *created county row*)
ASSESSMENT Functionality Detail
Type | Name | Task
BUTTON | submitBtn | Save fields to DB
FIELD
FIELD
FIELD
FIELD
FIELD

## QuestiontoDB Schema
ref | Location | Question | DB
| SELL | Name | DB(Table: Contacts, Column: Name).
| SELL | County | DB(Table: Properties, Column: Name).
| SELL | State | DB(Table: Properties, Column: State).
| SELL | Phone | DB(Table: Contacts, Column: phone).
| SELL | Email | DB(Table: Contacts, Column: email).
| ASSESSMENT | Name | DB(Table: Contacts, Column: Name).
|  | Phone | DB(Table: Contacts, Column: phone).
|  | Email | DB(Table: Contacts, Column: email).
|  | preferredCommMethod | DB(table: Contacts, Column: prefCommMethod)
How did you hear about us? Letter - ref code, other - more info
Is this contact the owner?
yes
|  |  |  | mailing address | DB(Table: Contacts, Column: streetAddressL1).
|  |  |  | city | DB(Table: Contacts, Column: city).
|  |  |  | state | DB(Table: Contacts, Column: state).
|  |  |  | zip | DB(Table: Contacts, Column: zip).
no (if no, create a new contact)
|  |  |  | owner name | DB(Table: Contacts, Column: Name).
|  |  |  | phone | DB(Table: Contacts, Column: phone).
|  |  |  | email | DB(Table: Contacts, Column: email).
|  |  |  | mailing address | DB(Table: Contacts, Column: streetAddressL1).
|  |  |  | city | DB(Table: Contacts, Column: city).
|  |  |  | state | DB(Table: Contacts, Column: state).
|  |  |  | zip | DB(Table: Contacts, Column: zip).
okay to contact owner?
|  | APN/ADN/Tax ID/ Parcel ID | DB(Table: Properties, Column: APN)
|  | Size of property? | DB(Table: Properies, Column: size)
estimated land value
your best asking price?
how long have you owned this property?
how did you acquire this property?
owned free and clear?
no - total owed
|  | road access | DB(Table: Properties, Column: roadAccess)
yes
paved
unpaved
easement
no-landlocked
|  | Utilities? | DB(Table: Properties, Column: Utilities)
electric
garbage
gas
phone
sewer
water/well
listed with a realtor?
anything else we should know?